## Change log
Date | Finding ID | Change made | Before | After | Evidence file | Performed by
2026-10-28 | Prep | Created unlicensed break-glass account breakglass2 with Global Administrator and MFA | 1 dedicated Global Admin (admin) | 2 dedicated Global Admins | Not captured | Blandine Ngwing-Allah
2026-10-28 | Prep | Downloaded firewall config backup before changes | No backup | D5-01-config-before.xml stored offline | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-01 | Deleted WAN rule "Testing" (any to any), applied changes | Pass any to any, seq 311 | Rule removed; default deny applies | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-02 | Deleted WAN rule "Temp remote access" (TCP 3389) | Pass any to 192.168.1.126:3389 | Rule removed | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-03 | Removed Global Administrator from Daniel Kim | Global Admins: admin, Daniel Kim | Global Admins: admin, breakglass2 | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-04 | Deleted WAN rule "Old client file transfer" (TCP 21) | Pass any to 192.168.1.126:21 | Rule removed | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-05 | Removed Sofia Alvarez from Finance and HR | Member of Design-Team, Finance, HR | Member of Design-Team only | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-06 | Deleted Anyone edit link on Invoices-2026.xlsx; set org sharing to New and existing guests, default Specific people, View | Anyone link with edit; org sharing Anyone; default Edit | No Anyone link; org sharing New and existing guests; default View | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-07 | Ran MFA registration campaign for all users | 3 of 17 MFA capable | Registration enforced at next sign-in | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-08 | Deleted stale guest Alex Reed | Pending guest in Design-Team | Guest removed | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-09 | Removed Taylor Morgan from Design-Team | Member of Client-Projects and Design-Team | Member of Client-Projects only | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-10 | Limited guest invites to admin roles; cleared owner-added guests in Microsoft 365 Groups | Anyone can invite; owners can add guests | Admin roles only; owners cannot add guests | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-11 | Teams external access set to client domains only; unmanaged accounts off | All domains allowed; unmanaged accounts on | Allowed list only; unmanaged accounts off | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-12 | Set Finance, HR, Management, Design-Team, IT-Support sites to Only people in your organization | External sharing On for all sites | External sharing on Client-Projects only | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-13 | Meeting policy: anonymous users verified and wait in lobby; presenters limited to org and guests | Anonymous join unverified | Anonymous join verified, lobby enforced | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-14 | Removed Taylor Morgan direct edit share on Acme-Rebrand | Direct share, Can edit | Access through Client-Projects only | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-15 | Removed Business Premium license from admin | Licensed with mailbox | Unlicensed; 12 of 25 licenses used | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-16 | Deleted the 2 disabled default LAN rules | 2 disabled rules in list | LAN list: anti-lockout, DNS, web only | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-17 | Set Pixelnestlab org-wide team to Private | Public | Private | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-18 | Restricted shared channel creation and external invites to owners | Any user can create; external invites on | Owners only | Not captured | Blandine Ngwing-Allah
2026-10-28 | F-19 | Updated OPNsense 26.7 to 26.7.5; limited GUI listen interface to LAN | 26.7; GUI on all interfaces | 26.7.5; GUI on LAN only | Not captured | Blandine Ngwing-Allah
2026-10-28 | Post | Downloaded firewall config backup after changes |  | D6-config-after.xml stored offline | Not captured | Blandine Ngwing-Allah
After screenshots were not captured. Evidence folders hold the before state.